## Slide 1
Synapse AI
Checkpoint 1
Arizona State University
ACCOMPLISHMENTS (KPIs)
Data Integration Complete
MIMIC-IV + Neo4j graph + ChromaDB operational
Core Pipeline Deployed
Hybrid retrieval + multimodal vision agent with BiomedCLIP
4-Brain Architecture Integrated
Vision, Knowledge Graph, Vector Search, Patient Context unified
Anti-Hallucination Framework
Structured confidence (HIGH/LOW), sigmoid reranking, Visual-RAG checks
NEXT TASKS (Rolling Action Items)
Task
Owner
Due
Priority
Reranking layer + dynamic thresholding
Member 1, Member 2
Mar 8
HIGH
Safety critic (independent model)
Pragyan
Apr 2
HIGH
SOAP note generator
Member 4
Apr 2
MED
Source-grounded generation
Member 5
Apr 2
MED
RISKS & BARRIERS
HIGH
Vision API Hallucination Rate
Free-tier models hallucinate 20-30% of CXR findings; no local classifier to cross-validate yet
MED
Evaluation Subjectivity
No gold-standard test set defined; clinical accuracy metrics require domain expert review
MED
Free-Tier API Rate Limits
OpenRouter free models throttle during batch evaluation; may delay quantitative benchmarks
MED
SCHEDULE
Feb 19
Core Pipeline delivered (hybrid retrieval + vision agent)
Mar 8
Reranking Integration complete (cross-encoder + thresholding)
Mar 20
Safety Layer initial implementation + independent critic
Apr 2
Checkpoint 2: Safety Layer + SOAP notes complete
Apr 20
Final Delivery: Evaluation benchmarks + user study + report
Team Alabama | Arizona State University | FSE 570
Checkpoint 1