## Slide 1
TrustMed AI
Checkpoint 2 Quad Chart
Neuro-Symbolic Clinical Decision Support
ACCOMPLISHMENTS (KPIs)
Data Integration Complete
MIMIC-IV + Neo4j graph + ChromaDB operational
Core Pipeline Deployed
Hybrid retrieval + multimodal vision agent with BiomedCLIP
4-Brain Architecture Integrated
Vision, Knowledge Graph, Vector Search, Patient Context unified
Benchmarked Vision & LLM Models
A/B testing on vision and LLM models for segmentation, captioning, abnormality ID
Fallback Mechanism
Do No Harm fallbacks with LLM safety override
ROLLING ACTION ITEM LIST
#
Action Item
Owner
1
Validate MIMIC schema and Neo4j nodes
KG Lead
2
Integrate image captioned reasoning with clinical text context
Vision Agent Dev
3
Patient context + history → generate SOAP notes
ML NaN
4
Performance testing within system architecture
5
Define deterministic safety triggers & override rules
RISKS & BARRIERS
HIGH
Schema Misalignment
MIMIC tables vs Neo4j graph misalignment → incorrect patient context retrieval
HIGH
Multimodal Reasoning Conflicts
Image captions vs clinical text produce inconsistent diagnoses
HIGH
SOAP Generation Hallucinations
Incomplete patient context causes fabricated content in SOAP notes
MED
Pipeline Latency
Combined vision + graph + vector + LLM processing increases response time
MED
Safety Trigger Calibration
Over-sensitive triggers block valid answers; under-sensitive ones miss unsafe responses
SCHEDULE TO CHECKPOINT 2 (Apr 2)
Feb 19
Mar 5
Mar 20
Apr 2
Apr 20
TODAY
MIMIC + Neo4j Validation
Vision-Text Integration
SOAP Note Generator
Safety Critic Layer
Performance Testing
Final Eval & Report
CP2
FINAL
Pragyan Borthakur | Arizona State University | Capstone Project
Checkpoint 2 | April 2026